## Daily Progress (hidden)
2021-07-28
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper
2021-07-29
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper
2021-07-30
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper
2021-08-02
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper
Update SIT Script sesuai dengan Alamat FTP dari User | [9 empty] | alamat FTP baru di infokan sore hari, sehingga Developer perlu testing ulang, setelah itu QA akan update sit script dan testing ulang
2021-08-04
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper
2021-08-20
Module | Progress Sebelumnya |  |  | Progress Hari ini |  |  | Defect |  |  | Kendala
| Test Case | Tested | Percentage | Test Case/Testing | Tested | Percentage | Minor | Major | Stopper

## Tasklist
NO | No result | Task Name | tester | Testing | script | Progress % | Developer | Unit test sudah
1 | [7 empty] | script + Result Done
2 | [7 empty] | On Progress
3
4
5
6
|  |  | total | 0 | 0 | #DIV/0!

## Summary
Summary Table of WMS (Wealth Management System) CIMB Defect Log
Severity | Defect Status Web Application | [5 empty] | Total Issue
| Raised | Answered | Retest | Open | Fixed | Closed
1-Showstopper | 1 | 0 | 1 | 3 | 0 | 7 | 12
2-Major | 10 | 0 | 1 | 9 | 0 | 47 | 67
3-Minor | 4 | 2 | 0 | 14 | 0 | 41 | 61
4-Saran | 1 | 2 | 0 | 1 | 0 | 9 | 13
Total | 16 | 4 | 2 | 27 | 0 | 104 | 153

## Summary Detail (hidden)
Summary Detail Table of WMS (Wealth Management System) CIMB Defect Log
No | Nama Project | Test Case | Nama Developer | Severity | Defect Status Web Application | [5 empty] | Total Issue
[5 empty] | Raised | Answered | Retest | Open | Fixed | Closed |  | Total Test Case
|  |  |  | 1-Showstopper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
|  |  |  | 2-Major | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 3-Minor | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 4-Saran | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Defect Log
Legend
[7 empty] | Defect Group | Defect Category | Severity | Keterangan | [5 empty] | Defect Status
[7 empty] | Definition | Requirement Error | 1-Showstopper | Sytem Tidak bisa digunakan/Tidak berfungsi | [5 empty] | Open
[8 empty] | Biz Parameter | 2-Major | System berfungsi, namun beberapa modul Tidak berjalan | [5 empty] | Raised
Project Name |  | goAML Product | [5 empty] | Program | 3-Minor | Minimal Impact atau Cosmetic Error | [5 empty] | Retest
Project ID | [6 empty] | Quality | Interface | 4-Saran | [6 empty] | Fixed
Project Manager | [7 empty] | Data | [7 empty] | Closed
Testing Management | [7 empty] | Access & Control | [7 empty] | Assigned
CRF No. | [7 empty] | Conversion | [7 empty] | Answered
[8 empty] | Internet Browser | [7 empty] | Saran
Defect ID | Menu | Keterangan | Browser / Handset | Defect Category Group | Defect Category | Defect Status | Severity | Raised by | Date Raised | PICTURE (Sheet) | DEV | Assigned to | Target Date Bugfix | Date Re-tested | Date Closed | Comment
1 | goAML - Report CTR - Edit - Delete Transaksi | Ada 1 Transaksi lalu Delete transaksi muncul error "Object cannot be cast from DBNull to other types", Transaksi tetap terhapus Report ID: 20695 | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-07 | Sheet1!A1
2 | goAML - Report CTR - Edit - Delete Transaksi | [Saran] Setelah transaksi di delete seharusnya Validation Result untuk Transaksi tersebut juga hilang Report ID: 30935 Update 081221: setelah coba di delete transaksi id 20, validation resultnya masih ada | Mozilla | Quality | Program | Closed | 4-Saran | Cici | 2021-12-07 | Sheet1!A1
3 | goAML - Report CTR - Edit | [Saran] Field Report Code di form Edit sebaiknya di disable Report ID: 30949 | Mozilla | Quality | Program | Closed | 4-Saran | Cici | 2021-12-07 | Sheet1!A1
4 | goAML - Report CTR - Edit - Add Transaksi | [Hanya Firefox] Field set from dan To di Firefox memanjang ke bawah, di chrome aman Report ID: 30949 | Mozilla | Quality | Interface | Closed | 3-Minor | Cici | 2021-12-07 | Sheet1!A1
5 | goAML - Report CTR - Edit - Add Transaksi | [Saran] Field Instrument Transaksi harusnya sudah otomatis diisi, jika sudah isi Transaction Method Report ID: 30949 | Mozilla | Quality | Program | Closed | 4-Saran | Cici | 2021-12-07 | Sheet1!A1
6 | goAML - Report CTR - Edit - Add Transaksi | Case: SETOR: Sender Type Person, pertama klik Search Customer -> Cancel -> klik Search Non Customer pada Pop Up Search Non customer masih ada data dari Pop Up search Customer Report ID: 30949 | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2021-12-07 | Sheet1!A1
7 | goAML - Report CTR - Edit - Add Transaksi | Case: SETOR From: klik search non customer lalu select. Data Address, Phone, Identity tidak muncul di Grid Address, Phone, Identity Person. Padahal data tersebut ada Jika Klik Edit lagi baru muncul data Address, Phone, Identity Person Report ID: 30949 | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-07 | Sheet2!A1
8 | goAML - Report CTR - Edit - Add Transaksi | Case: Klik Search Non Customer -> pilih salah satu wic - lalu saya Cancel setelah klik cancel name sendernya ada dan ketika klik edit datanya ada Saran harusnya kalau klik Cancel Field Name Sender tidak keiisi dan form person nya juga gak keisi Report ID: 30949 | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-07 | Sheet2!A1
9 | goAML - Report CTR - Edit - Add Transaksi | Case: SETOR To: klik search account lalu select. Data Signatory tidak muncul di Grid Signatory. Padahal data tersebut ada Jika Klik Edit lagi baru muncul data Signatory Report ID: 30949 | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-07 | Sheet2!A1
10 | goAML - Report CTR - Edit - Add Transaksi | [Saran] Field set informasi pengirim/penerima sebaiknya muncul ketika sudah pilih sender /recipent type, menghindari kesalahan user ketika klik edit tapi blm pilih sender /recipent type Report ID: 30949 | Mozilla | Quality | Interface | Answered | 4-Saran | Cici | 2021-12-07 | Sheet2!A1 | [5 empty] | Sudah ada validasinya saat klik Edit
11 | goAML - Report CTR - Edit - Detail Transaksi | [Saran] Button Edit di field set Pengirim/Penerima sebaiknya diganti jadi Detail Report ID: 30949 Update 13/12/2021: setelah di cek button editnya masih ada dan pas saya test, datanya bisa di edit walaupun transaksi nya tidak bisa di save, sarannya button edit nya dihilangkan saja | Mozilla | Quality | Interface | Closed | 4-Saran | Cici | 2021-12-07 | Sheet3!A1
12 | goAML - Report CTR - Edit - Add Transaksi | Search Customer -> Select lalu save No CIF tidak muncul di Field CIF ¦ Account No: Report ID: 30949 | Mozilla | Quality | Program | Answered | 3-Minor | Cici | 2021-12-07 | Sheet3!A1 | [5 empty] | CIF & Account No hanya tampil untuk Type Account. Karena kalau Person tidak ada field untuk nampung data tersebut.
13 | goAML - Report CTR - Edit - Add Transaksi | Add Conductor -> Search WIC Pop Up Search WIC muncul data CIF Report ID: 30949 | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2021-12-07 | Sheet3!A1
14 | goAML - Report CTR - Edit - Add Transaksi | Case: Add Conductor -> klik search non customer lalu select. Data Address, Phone, Identity tidak muncul di Grid Address, Phone, Identity Person. Padahal data tersebut ada (seperti defect no 7) Report ID: 30949 | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2021-12-07
15 | goAML - Report CTR - List of Generated | View List of Generated kosong, padahal ada Report CTR yang valid | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-08 | Sheet4!A1
16 | goAML - Report CTR - Edit - Add Transaksi | Case: SETOR From Entity NotMyClient To Account MyClient 1. Isi From Entity Not My Client saya hanya isi field Coorporate Name 2. Lalu isi To Account My Client -> Search Account -> Save 3. Pas di cek data From Director Entity nya keisi director To, padahal sebelumnya gak isi director | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-08 | Sheet4!A1
17 | goAML - Report CTR - Edit | [Saran] Field Report Code yang sudah di Disable, bisa dihapus value nya, sehingga pas save report ketahan Validasi "Report Code is Required" seharusnya value nya tidak bisa dihapus | Mozilla | Quality | Program | Closed | 4-Saran | Cici | 2021-12-08 | Sheet4!A1 | [5 empty] | Yang ini sedang dicari cara untuk hide button erasernya. Sudah pake berbagai cara malah bikin error javascript. Sudah diganti jadi DisplayField
18 | goAML - Report CTR - Edit - Edit Transaksi | Pada Detail Informasi Pengirim dan Penerima masih ada button Save, kalau detail harusnya cuma "Back" | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2021-12-13 | Sheet5!A1
19 | goAML - Report CTR - Add | [Saran] Report Code di filter sesuai Jenis Laporan | Mozilla | Quality | Program | Answered | 4-Saran | Cici | 2021-12-16 | Sheet6!A1 | [5 empty] | Later ya... mau ngejerin yg Case Management dulu [11-03-22] Done
20 | Global Parameter PK 3002 | Saat Edit Data -> lalu Reject, report yang di reject hilang dari View, harusnya Report nya ttap ada tapi datanya tidak berubah | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-16 | Sheet6!A1
21 | goAML - Report CTR - Add | Case: Add Report tanpa isi transaksi 1. Isi Form Report 2. klik add transaksi (gak isi transaksi) lalu klik cancel 3. klik menu lagi (tanpa klik back and save draft) 4. report terbentuk dengan status draft (ID 31022), ketika klik detail dan delete ada error "Object cannot be cast from DBNull to other types." [Saran] kalau gak klik Save atau Back and save draft, sebaiknya reportnya gak terbentuk | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2021-12-27
22 | goAML Report View | Di HSBC, di form Advanced Filter, |  |  |  | Closed
23 | goAML - Report STR - View Excel - Export Current Page Excel - Export All Page CSV - Export Current Page Excel - Export All Page | Urutan data hasil Export tidak sama dengan View, sarannya samakan urutan dengan View | Mozilla | Quality | Interface | Closed | 3-Minor | Cici | 2022-03-09 | STR 1 | [5 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ
24 | goAML-Report STR-View-Edit Report ID 34791 Status Report "2-Waiting for upload Ref No" | Delete salah satu Transaksi, status tidak berubah, status harusnya berubah jadi "In Progress Editing" | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2022-03-09 | STR 6 | [5 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ
25 | goAML - Report CTR - View - Add New Record | di Pilihan Dropdown Report Code , Semua Report Code muncul tidak di filter sesuai report nya CTR | Chrome | Quality | Program | Raised | 3-Minor | Mia | 2022-03-09 | CTR11!A1 | [5 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ
26 | goAML-Report STR-View-Advanced Filter | klik adavnced filter up advanced filter tidak muncul pop. Error juga tidak muncul | Mozilla | Quality | Program | Raised | 2-Major | Cici | 2022-03-10 | STR 18 | [5 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ
27 | goAML - Report CTR - View - Add New Record | Di action detail From dan To, (Add, edit, delete) phone, adress, identification dll masih berfungsi seharusnya hanya read only | Chrome | Quality | Program | Raised | 2-Major | Mia | 2022-03-09 | CTR13!A1 | [5 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ [11-03-22] PENDING
28 | goAML - Report CTR - View - Delete | setelah berhasil delete Report muncul you dont have permission to access this module, harusnya kembali ke view | Mozilla | Quality | Access & Control | Closed | 2-Major | Mia | 2022-03-10 | CTR 20!A1 | [5 empty] | [11-03-22] CLOSED
29 | goAML - (Report IFTI, Report CTR, Report STR) - List Of generate | biasanya jika tanggal (Transcation date , Last update date, Last generate date) di kolom nya ada icon pick tanggal seperti di form lain | Mozilla | Quality | Interface | Closed | 4-Saran | Mia | 2022-03-10
30 | goAML - (Report IFTI, Report CTR, Report STR) - List Of generate | Searching di kolom Validate schema Result tidak berfungsi untuk inputan 2 contoh: 2 | Mozilla | Quality | Program | Closed | 2-Major | Mia | 2022-03-10
31 | goAML - (Report IFTI, Report CTR, Report STR) - List Of generate | Searching di kolom Already Validate schema tidak berfungsi untuk inputan no / yes tetapi input 1 akan tampil data yes | Mozilla | Quality | Program | Closed | 2-Major | Mia | 2022-03-10
32 | goAML - Report IFTI - List Of generate IFTI | Advanced Filter, tidak tampil pilihan filter sql nya | Mozilla | Quality | Program | Closed | 3-Minor | Mia | 2022-03-10
33 | goAML - Report CTR - List Of generate CTR - Excel Current Page | 1. List of generate ctr, hasil export file excel current page terdapat kolom report type yang tidak ada di view 2. Kolom status API berada di Urutan Terakhir, sedangkan di View terdapat di Sebelah Kanan Status 3. Hasil Export Current Page terdapat 28 data, sedangkan dalam 1 page ada 25 data | Mozilla | Quality | Program | Closed | 2-Major | Mia | 2022-03-10
34 | goAML - Report CTR - List Of generate CTR - Excel All Page | 1. List of generate ctr, hasil export file excel All page terdapat kolom report type yang tidak ada di view 2. Kolom status API berada di Urutan Terakhir, sedangkan di View terdapat di Sebelah Kanan Status | Mozilla | Quality | Program | Closed | 2-Major | Mia | 2022-03-10
35 | goAML - Report CTR - Approval - Excel Current Page & All Page | 1. Hasil file yang terdownload, headernya masih menggunakan nama tabel bukan Label name di halaman approval 2. ada beberapa kolom yang ada di file hasil download tetapi tidak ada di halaman approval, dan tidak berurutan | Mozilla | Quality | Program | Closed | 3-Minor | Mia | 2022-03-10 | [6 empty] | [11-03-22] CLOSED
36 | goAML - Report CTR - Approval - CSV Current Page & All Page | 1. Hasil file yang terdownload, headernya masih menggunakan nama tabel bukan Label name di halaman approval 2. ada beberapa kolom yang ada di file hasil download tetapi tidak ada di halaman approval, dan tidak berurutan | Mozilla | Quality | Program | Closed | 3-Minor | Mia | 2022-03-10 | [6 empty] | [11-03-22] CLOSED
37 | goAML - Report IFTI - View - Edit | Edit Report – Detail Transaksi – Detail Account Di action detail From dan To, (Add, edit, delete) phone, adress, identification dll masih berfungsi seharusnya hanya read only | Mozilla | Quality | Program | Raised | 2-Major | Mia | 2022-03-10 | [6 empty] | Defect From BTPN https://nawadata0.sharepoint.com/:x:/s/NawadataMPP/Ed1m8AGVa7RLoO6rg-VrYQIBEwUOAV4b4w2Epy_3xoMltQ [11-03-22] PENDING
38 | goAML - Report CTR -Add New Record | Case: Add Report Add TRX klik menu kiri Status nya berubah jadi draft tapi Valid (Yes) harusnya status validnya NO Record nya juga ada di halama terakhir | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2022-03-11 | [6 empty] | [11-03-22] CLOSED
39 | goAML - Report CTR -Edit | Case: Waiting for Generate ¦ Yes Edit Reject Cek Diview jadi Waiting for Generate ¦ Yes | Mozilla | Quality | Program | Closed | 3-Minor | Mia | 2022-03-11
40 | goAML - Report STR -Add | Add New Record Approval History ada 3 | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-03-11
41 | ANZ- Audit Trail | Created By dan Approved By nama nya sama | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-03-11
42 | goAML STR - View Result dari Upload STR | setelah berhasil upload STR, Field Tanggal Laporan tidak keisi sesuai dengan field Tanggal Laporan pada template yang diupload. Tanggal Laporan terisi dengan tanggal upload str Tanggal Transaksi di View terisi dengan tanggal laporan pada template str [Saran] ubah nama field pada template | Mozilla | Quality | Program | Raised | 4-Saran | cici | 20-04-2022 | Sheet8!A1 | [5 empty] | Di code SP : Tanggal laporan di excel itu, masuk ke Transaction Date kalo submission Date, dia ambil getdate() Paling kalau mau diubah nama header di excelnya, dari Tanggal laporan -> Tanggal transaksi. Note : jadi karena STR itu, di transaksinya bisa campur" tanggal (kalo CTR ama IFTI, pasti 1 tanggal). Jd di excel nya put 1 tanggal asal aja, buat masukin ke Report field Transaction Date. Sebenernya ini tidak dipakai / tidak mencerminakn, karena transaksinya bisa campur"
43 | goAML STR - View Result dari Upload STR | Status Report "Waiting for Generate" tapi Is Valid "No" dan ada Error Message | Mozilla | Quality | Program | Closed | 2-Major | cici | 20-04-2022 | Sheet8!A1
44 | Upload STR - Detail Detail Record yang di Reject | Error "Invalid Column Name fk_report_id" untuk detail report yang di reject | Mozilla | Quality | Program | Closed | 1-Showstopper | cici | 20-04-2022 | Sheet8!A1
45 | goAML - Report CTR -Edit | Case: Edit Report Approve Edit Lagi Error "There is Already Save State for this Report ID" | Mozilla | Quality | Program | Raised | 2-Major | BTPN | 27-05-2022 | Sheet9!A1 |  | Ari |  |  | 31-05-2022
46 | goAML - List of Generate | Saat generate dengan beda reporting person di xml nya reporting person nya gak keganti | Mozilla | Quality | Program | Raised | 2-Major | BTPN | 27-05-2022 |  |  | Felix |  |  | 31-05-2022
47 | goAML-Approval | View approval nya dimunculkan per role | Mozilla | Quality | Program | Raised | 2-Major | BTPN | 27-05-2022 |  |  | Felix |  |  | 31-05-2022
48 | goAML - Report STR - Add New Record- Add Activity - Add Account goAML - Report STR - Edit - Add Activity - Add Account | Error "Object No Reference" saat add Account" | [5 empty] | Cici
49 | goAML - Report CTR -Edit | (case : jika save tanpa melakukan edit/perubahan) diberi pop up konfirmasi lakukan perubahan terlebih dahulu saat klik button save contoh : "There is not Changes Data. Please Edit First before Saved." | Chrome | Quality | Interface | Raised | 3-Minor | Evola | 30-08-2022
50 | goAML - Report IFTI - Validate Schema | Muncul pesan error “The 'email' element is invalid - The value 'email' is invalid according to its datatype 'email_address' - The Pattern constraint failed.” untuk Unique Reference = TEST-3108-1547, sedangkan pada saat report (Unique reference = TEST-3108-1547) dicek, field email kosong dan memang tidak mandatory diisi | Chrome | Quality | Program | Raised |  | Evola | 31-08-2022 | Sheet11'!A1
50 | goAML - Report STR - Add New Record (Record Code = LTKM - Atas Permintaan PPATK) | Field/text box PPATK FIU Ref. Number dibuat menjadi field mandatory | Chrome | Quality | Program | Raised | 3-Minor | Evola | 2022-01-09 | Sheet12'!A1
51 | goAML - Report CTR - Edit - Add Transaksi | Case: SETOR From Entity MyClient To Account Entity MyClient 1. Isi From Entity Not My Client lalu add direktor phone dan address 2. Lalu isi To Account My Client, cek direktor phone and address ada data direktor phone dan address from 3. delete data tersebut, data direktor from kehapus semua | Mozilla | Quality | Program | Closed | 2-Major | BTPN (Dimas) | 2022-09-23 |  |  | Felix
52 | goAML - Report CTR - Edit - Add Transaksi - From Entity | Add Phone dan Address Director data yang ada sebelum nya hilang, yang muncul hanya data yang di add | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2022-09-26 |  |  | Felix
53 | goAML - Report CTR - Edit - Add Transaksi | Saat Save transaksi ketahan Validasi From Entity Addresss dan Phone Director harus diisi, padahal datanya sudah diinput | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2022-09-26 |  |  | Felix
54 | goAML - Report CTR - Approval | Transaction Location masih mandatory | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2022-09-26 |  |  | Felix
55 | goAML - Report CTR - Edit - Add Transaksi | Fix jika isi data account menggunakan Search Account, Phone Account Director Entity, masuk ke Signatory Phone | Mozilla | Quality | Program | Closed | 2-Major | BTPN (Dimas) | 2022-09-28 |  |  | Felix
56 | goAML - Report CTR - Edit - Add Transaksi | Fix Bug jika Add Transaction : Search Customer dan Search Account, data Director Identification tidak tampil | Mozilla | Quality | Program | Closed | 2-Major | BTPN (Dimas) | 2022-09-28 |  |  | Felix
57 | goAML - Data - Account - Edit | Edit data kena validasi "Account closed date must greater than or equal balance date" padahal field Account closed date kosong. seharusnya tidak kena validais | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-10-05 |  |  | Ari
58 | goAML - Report - Generate STR | Generate STR CIF 1101407001 Select Transaksi Ref Num SETOR1-19 dan SETOR2-20 Save Approval - Reject Error Underlaying provider failde on rollback | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-05 |  |  | Ari
59 |  | Grid Transaction Data dikasi paging | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-10-05 |  |  | Ari
60 |  | Data direject tidak ada status | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-10-05 |  |  | Felix
61 | goAML - Report - Generate STR | Transaction Ref No mandatory tapi tidak ada validasi *harusnya tidak mandatory | Mozilla | Quality | Program | Closed | 3-Minor |  | 2022-10-05
62 | goAML - Report - STR | View STR - Tanggal transaksi, ketika data di delete, tanggal transaksi gak update | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-05
63 | goAML - Report - CTR - Edit | CTR -> Edit -> Add Transaction : From Account Entity to Entity From Account entity Add Manual Director, To Entity Add manual director work place phone double (kadang2) | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-14
64 | goAML - Report - CTR - Edit | CTR -> Edit -> Add Transaction : From Account Entity to Entity From Account entity Add Manual Director, To Entity Add manual director , Save transaksi -> kena validasi from director gak ada, pas di add lagi muncul data yg udah di add sblm nya, to juga | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-14
65 | goAML - Report - STR - Add | STR PBK Add New Record From Account to Account -> pas add to director data phone (dan grid2 lainnya) lalu save data dari from akan muncul | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-14
66 | goAML - Report - MultiParty | Multiparty STR-> add multiparty -> myclient->search account->korporasi ->lalu edit-> pilih individu->save kena validasi utk korporasi director | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-14
67 | goAML - Report - MultiParty | Multiparty STR-> add multiparty -> myclient->search account-> pilih individu->save -> add multiparty data party nya muncul data individu yang udh di add sblmnya | Mozilla | Quality | Program | Closed | 2-Major |  | 2022-10-14
68 | goAML - Data - Customer - Edit | Issue tidak bisa save saat edit pada cif di Query berikut: select * from goAML_Ref_Customer a where convert (varchar(max), PK_Customer_ID) in (select ModuleKey from ModuleApproval x) saat save kena validasi data di pending approval padahal di approval gak ada | Mozilla | Quality | Program | Closed | 2-Major | Dimas | 2022-10-31 | Sheet15 |  | Felix |  |  |  | From Fama
69 | goAML - Report - goAML Report Validation Summary | saat klik invalid kena issue di "You dont have access to this module" | Mozilla | Quality | Program | Closed | 3-Minor | Dimas | 2022-11-01 | Sheet15 | [5 empty] | From Fama
70 | goAML - Parameter - General Parameter - Reporting Person | Edit lalu input telepon tempat bekerja, setelah approval tidak muncul datanya | Mozilla | Quality | Program | Closed | 2-Major | Dimas | 2022-11-01 | Sheet15 | [5 empty] | From Fama
71 | goAML - Report - Generate STR - Add - Reject | Generate TRX CIF 1101407001 (Range 010122-today) Centang 2 TRX Save Approve - Reject Cek Detail - > di grid transaction data ada 12 TRX (padahal tadi yg di centang 2) PK 1256 | Mozilla | Quality | Program | Closed | 2-Major | Dimas | 2022-11-03 | Sheet15 | [5 empty] | From Fama
72 | goAML - Report - STR - Add | Add Report, approve lalu "Need to Correction" status report Need to Correction tapi is valid "Yes" PK 52300 | Mozilla | Quality | Program | Answered | 3-Minor | Cici | 2022-11-03 | Sheet15 | [5 empty] | jd statusnya 5 - Need correction itu bisa karena 2 hal validasi data nya tidak valid.di suruh need to correction ama checker, walau validasi data valid
73 | goAML - Report - Report STR - View | Saat mengkoreksi/edit Transaksi dengan menambahkan Address dan Employer Address. data address/alamat yang di tambahkan tidak masuk | Chrome | Quality | Program | Closed | 2-Major | Dimas (Fama) | 2022-11-25 | 41!A1 |  | Daniel | 2022-11-29 | 2022-11-29 | 2022-11-29 | From Fama
74 | goAML - Data - Customer - Edit | Edit Customer Corp, kena validasi "Invalid Email Address in Email Korporasi" jika tidak diisi, padahal tidak wajib. | Chrome | Quality | Program | Closed | 2-Major | Dimas (Fama) | 2022-12-26 |  |  | Ari | 2022-12-26 | 2022-12-26 |  | From Fama
75 | goAML - Data - Account - Edit | Edit : Untuk Client Number dihilangkan validasi inputan "Number Only" | Chrome | Quality | Program | Closed | 2-Major | Dimas (Fama) | 2022-12-26 |  |  | Ari | 2022-12-26 | 2022-12-26 |  | From Fama
76 | goAML - Report - Report STR - MultiParty - Edit | Delete Multiparty (grid tidak refresh) | Chrome | Quality | Program | Closed | 2-Major | Dimas (Fama) | 2022-12-30 |  |  | Felix | 2022-12-30 | 2022-12-30 |  | From Fama
77 | goAML - Report - Report STR - MultiParty - Edit | Edit Transaction LTKM (yg di Mapping ke Bi-MultiParty), kalau datanya MutliParty, From To tetap muncul | Chrome | Quality | Program | Closed | 2-Major | Dimas (Fama) | 2022-12-30 |  |  | Felix | 2022-12-30 | 2022-12-30 |  | From Fama
78 | goAML - Report - Report STR | STR Multi Party: ada 2 trx: Edit Trx 1 -> ubah biparty ke multiparty Edit Trx 2 -> ubah ke multipary -> muncul data multiparty trx 1 | Chrome | Quality | Program | Closed | 1-Showstopper | Dimas (Fama) | 2023-01-03 |  |  | Felix | 2023-01-11 | 2023-01-11 |  | From Fama
79 | Goaml - Data - Costumer - View | Data di view ada 556, tetapi di deskripsinya beda ada 558 tidak sesuai dengan jumlah datanya | Chrome | Quality | Interface | Open | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A1 | Dev lama |  | 2023-02-23 | 2023-02-23
80 | Goaml - Data - Costumer - Add New Record ( Individu ) | Add new record menambahkan tanpa data, Type Person di kosongin dan klik save muncul validasi " Phone is required " Seharusnya => " Type Person is Required" | Chrome | Quality | Interface | Open | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A28 | Dev lama
81 | Goaml - Data - Costumer - Add New Record ( Individu ) | pada panel 1. Person PEP Add 2. Sanction Add 3. Related Person Add Field nya tidak sejajar | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A80 | Septian | Septian
82 | Goaml - Data - Costumer - Add New Record ( Individu ) | Pada Panel Sanction Add, Negative Case Valid From dan Valid To nya adalah mandatory. Ketika save tanpa menginput data pada field tersebut berhasil seharusnya muncul validasi | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A103 | Septian | Septian | 2023-02-23 | 2023-02-23
83 | Goaml - Data - Costumer - Add New Record ( Individu ) | - Relation Person Add Untuk Nationality lebih baik 1 field saja yang mandatory yaitu Nationality 1 karena ada saja person/orang yang tidak memiliki sampai 3 nationality | Chrome | Quality | Interface | Closed | 4-Saran | Tiarma | 2023-02-21 | Sheet16!A121 | Septian | Septian
84 | Goaml - Data - Costumer - Add New Record ( Korporasi) | Negative Case (Relation Person Add, Person PEP add, Sanction Add, Relation Person Add, Entity Identification Add) Ketika kosongin data pada field Relation Data Range => muncul validasi " Object Variable or with block variable not set " Seharusnya " Relation Data Range valid To is Required " dst | Chrome | Quality | Data | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A143 | Septian | Septian | 2023-02-23 | 2023-02-23
86 | Goaml - Data - Costumer - Add New Record ( Individu ) | Ada Typo pada kata - Related Entties - Address Typet | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A188 | Septian | Septian
87 | Goaml - Data - Costumer - Add New Record ( Individu ) | Pada Field Share Percentage => -1.79, seharusnya 0 atau kosong | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A210 | Septian | Septian | 2023-02-23 | 2023-02-23
88 | Goaml - Data - Costumer - Add New Record ( Individu ) | Director kosongin domicile country setelah disubmit muncul validasi " Residence is required ". padahal residence since itu sudah di input seharusnya => domicile country | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A230 | Dev lama
89 | Goaml - Data - Costumer - Add New Record ( Korporasi) | kosongin identification type muncul vailidasi Document Type seharusnya identification Code | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-21 | Sheet16!A258 | Dev lama
90 | Goaml - Data - Costumer - Add New Record (Individu/Korporasi) | Untuk bagian Validasi, muncul secara berurutan jika field nya nya dikosongin. Nama Field nya sesuai dengan yang muncul di validasi Dan jika dia field mandatory sebaiknya diberi warna | Chrome | Quality | Interface | Closed | 4-Saran | Tiarma | 2023-02-21 |  | Dev lama
91 | Goaml - Data - Costumer - Add New Record (Individu/Korporasi) | Field yang dihapus/di hide 1. Individual Customer - Foreign Language Full Name - Country of Birth 2. Related Person - Relation Data Range - Valid From - Relation Data Range - Is Approx From Date? - Relation Data Range - Valid To - Relation Data Range - Is Approx To Date? - Full Foreign Name - Residence Since 3. Corporate Customer - Entity Status - Entity Status Date 4. Related Entities - Relation Data Range - Valid From - Relation Data Range - Is Approx From Date? - Relation Data Range - Valid To - Relation Data Range - Is Approx To Date? - Entity Status - Entity Status Date | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-24 | Sheet16!A291 | Septian | Septian
92 | Goaml - Data - Costumer - Approval | Pada Detail data pada Approval sebaiknya dikasih button detail setiap panel supaya data nya bisa dibaca dengan jelas | Chrome | Quality | Interface | Open | 4-Saran | Tiarma | 2023-02-24 | Sheet16!A370 | Septian | Septian
93 | Goaml - Data - Costumer - View | Tabel kosong terdapat di detail data seperti Entity Identification, Sanction, Related Person, Related entities seharusnya tidak ada Button Detail berada diujung sebelah kanan, seharusnya dikiri | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-02-24 | Sheet16!A398 | Septian | Septian |  | 2023-05-03 | 2023-05-03
94 | goAML - Data - Customer- Individu - Related Person | Field: First Name, Middle Name, Prefix, Country of Birth dihilangkan saja karna sesuai skema tidak di gunakan | Chrome | Quality | Data | Closed | 3-Minor | Tiarma | 2023-03-03 | Sheet16!A426 | Septian | Septian |  | 2023-05-03 | 2023-05-03
95 | goAML - Data - Customer- Export All/Current Page | Ubah nama file name hasil download jadi nama modul contoh Daftar Customer. untuk sekarang nama file nya masih download xlsx | Chrome | Quality | Interface | Open | 3-Minor | Tiarma | 2023-03-03 | Sheet16!A447 | Dev lama
96 | GoAML - Data - Customer | Sesuai skema/list table field berikutt tidak mandatory Individu - Person PEP function name function Description Valid From Is Approx From Date Valid To Is Approx To Date comments - Sanction Add provider match criteria link to source Sanction List Attributes Valid From Is Approx From Date Valid To Is Approx To Date comments Related Person Tidak Mandatory - Gender - Title - First Name - Birth date - Birth place - Mothers name - Alias - SSN - Passport number - Passport country - Id number - Nationality 1 - Nationality 2 - Nationality 3 - residence - occupation - deceased - deceased date - tax number - tax reg number - source of wealth Entity Identification Add issue_date expiry_date issued_by comments | Chrome | Quality | Data | Raised | 2-Major | Tiarma | 2023-03-03 | Sheet16!A515 | Septian | Septian |  | 2023-05-03 |  | Masih belum fixed per 5 may 2023 Edited to Major - Alvin
97 | GoAML - Data - Customer | ubah label field jadi bahasa inggris -Customer Address Add Ibu Kota | Chrome | Quality | Interface | Closed | 3-Minor | Tiarma | 2023-03-03 | Sheet16!A447 | Dev lama |  |  | 2023-05-03 | 2023-05-03
98 | GoAML - Data - Customer - Individu | ketika di save, nama label nya berubah atau yang tampil tidak sama dengan label yang sudah di add sebelumnya Identification - Nomor - Jenis Dokumen Work Place Phone - Alat Komunikasi | Chrome | Quality | Data | Closed | 3-Minor | Tiarma | 2023-03-03 | Sheet16!A473 | Dev lama |  |  | 2023-05-03 | 2023-05-03
99 | goAML - Report - Report CTR - View | Edit Report Invalid - > Save -> Approve Cek di View Error Message untuk Report tersebut masih ada | Mozilla | Quality | Program | Closed | 3-Minor | Dimas (Fama) | 2023-02-23 |  | - | Felix | 2023-02-23 | 2023-02-23 | 2023-02-23 | After Rilis
100 | Proses Daily IFTI | Generate IFTI Non SWIFT: Data Signatory Identification, Address Employer dan Phone Employer tidak keisi Account No Penerima (sisi To) tidak keisi | Mozilla | Quality | Data | Closed | 2-Major | Cici | 2023-02-22 |  | Dari goAML Lama | Felix | 2023-02-22 | 2023-02-22 | 2023-02-22 | After Rilis
101 | goAML - Data - Account - Edit - Related Entities/Person/Account | [Saran] Button Search Customer/Search Non Customer di Hide di Detail Related Entities, Person dan Account Nama Panel di add, edit detail ubah jadi Related Entities (sebelumnya Related_Entities) Nama Panel di add, edit detail ubah jadi Related Person (sebelumnya Related_Person) Nama Panel di add, edit detail ubah jadi Related Account(sebelumnya Related_Account) | Mozilla | Quality | Interface | Closed | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
102 | goAML - Data - Account - Edit - Related Person | Field: First Name, Middle Name, Prefix, Country of Birth dihilangkan saja karna sesuai skema tidak di gunakan | Mozilla | Quality | Data | Open | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
103 |  | Saat Select Customer Field berikut datanya tidak keisi padahal di master datanya ada Pasport Country Nationality 1, 2, 3 Residence -> ganti nama field jadi Domicile Country Tax Number Source of Wealth Tax Reg Number -> ganti nama field jadi is PEP? (boolean) | Mozilla | Quality | Data | Open | 2-Major | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
104 | goAML - Data - Account - Edit - Related Account | Saat Select Account Field Open Date data tidak keisi padahal di master datanya ada | Mozilla | Quality | Data | Closed | 2-Major | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
105 | goAML - Data - Account - Edit - Sanctions | Hapus/Hide Field berikut (karna tidak digunakan di skema) Valid From Is Approx From Date Valid To Is Approx To Date | Mozilla | Quality | Data | Closed | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
106 | goAML - Data - Account - Approval | ubah label field jadi bahasa inggris hide panel sigantory -> gak jadi | Mozilla | Quality | Interface | Open | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
107 | goAML - Data - Account - Export All/Current Page | Ubah nama file name hasil download jadi nama modul contoh Daftar Account. untuk sekarang nama file nya masih download xlsx | Mozilla | Quality | Interface | Closed | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
108 | goAML - Data - Account - Edit | Account Korporasi Ubah Label Rekening Korporasi jadi bahasa inggris | Mozilla | Quality | Interface | Open | 3-Minor | Cici | 2023-03-01 | Sheet17 ¦ Account!A1 | Ari
109 | goAML - Data - Account - Edit - Sanctions | Pada Grid Sanction tampilkan kolom Nama dan Provider, Match Criteria, Account No dan comments hide aja | Mozilla | Quality | Interface | Open | 3-Minor | Cici | 2023-03-02 |  | Ari
110 | goAML- Data - WIC - Edit goAML- Data - WIC - Delete goAML- Data - WIC - Add | Terdapat Banyak Label yang belum dalam Bahasa Inggris | Chrome | Quality | Interface | Open | 3-Minor | Alvin | 2023-03-20 |  | Septian
111 | goAML - Data - WIC - Add | Terdapat interface Validasi Length pada Menu Add, dengan memunculkan warning bahwa length sudah melebihi yang ditetapkan. Ketika click save masih tetap lolos dari add masuk kedalam approval Ketika click approve pada approval akan memunculkan error "Validation failed for one or more entities. See 'EntityValidationErrors' property for more details" | Chrome | Quality | Program | Raised | 1-Showstopper | Alvin | 2023-03-24 | Defect | Septian |  |  |  |  | Root Cause: Karena belum implementasi validasi lenght
112 | goAML - Data - WIC - Edit | Edit data optional dan Mandatory -> Save -> tertahan validasi "There is No change data" Ketika "is real WIC" di centang pada entity dan person baru dapat di save atau ketika "is protected" di centang pada person baru dapat di save. Setelah berhasil ter Add Flag is Real WICnya akan kembali lagi ke false | Chrome | Quality | Data | Open | 2-Major | Alvin | 2023-03-27 | Defect | Septian
113 | goAML - Data - WIC - Add | Pada Informasi telepon dan informasi Alamat add field -> kosongkan mandatory-> save -> tidak muncul pop up required, namun hanya ada warning pada fieldnya | Chrome | Quality | Interface | Open | 2-Major | Alvin | 2023-03-27 | Defect | Septian
114 | goAML - Data - WIC - Add, Edit | Pada Form Entity bagian entity Identification mempunyai nama tabel yang tidak sesuai dengan dokumen, pada field dan tabel dinamakan "Country of birth", pada dokumen di nyatakan "Issue Country" atau "Negara Penerbit" | Chrome | Quality | Interface | Open | 2-Major | Alvin | 2023-03-27 | Defect | Septian
115 | goAML - Data - WIC - Add, Edit | Pada Form Entity bagian entity Identification mempunyai field Mandatory yang tidak sesuai dengan yang tercatat pada dokumen, Bukan merupakan field mandatory Field issue date, Expiry date, issued by dan comment | Chrome | Quality | Program | Open | 2-Major | Alvin | 2023-03-27 | Defect | Septian
116 | goAML - Data - WIC - Add | Ketika Melakukan Add Data pada Form Entity, sebaiknya semua column Action di letakan di Paling Kiri | Chrome | Quality | Interface | Saran | 4-Saran | Alvin | 2023-03-27 | Defect | Septian
117 | goAML - Data - WIC - Add, Edit | Sesuai skema/list table field berikut mandatory Person - Person PEP Pep Country - Sanction Add Sanction list name | Chrome | Quality | Program | Open | 3-Minor | Alvin | 2023-03-27 | Defect | Septian
118 | goAML - Data - WIC - Add, Edit | Sesuai Skema/List table field berikut tidak digunakan/ di hide Person - Person PEP Relation Date Range Type - Sanction Add Relation Date Range Type | Chrome | Quality | Program | Open | 3-Minor | Alvin | 2023-03-27 | Defect | Septian |  |  |  |  | Belum sinkron dengan info baru
119 | goAML - Data - WIC -Approval Delete | WIC Approval -> Approval Delete data -> accept approval Ketika sudah Accept untuk approval delete record akan muncul Error "The Underlying Provider failed on Rollback" dan tidak memunculkan pesan berhasil hapus record, record akan terhapus dari database tapi tidak mengarahkan ke view Approval Ketika di click accept kembali akan memunculkan error "Object Reference not set to an instance of an object" | Chrome | Quality | Program | Open | 1-Showstopper | Alvin | 2023-03-28 | Defect | Septian |  |  |  |  | Root Cause: 310323 sedang di debug
120 | goAML - Data - WIC - Add, Edit | View -> Add/ Edit Person -> delete informasi tempat bekerja -> yes akan memunculkan error "Can only enter one workplace address information" "View -> Add/ Edit Person -> delete informasi telpon tempat bekerja -> yes akan memunculkan error ""Can only enter one workplace phone information"" | Chrome | Quality | Program | Open | 1-Showstopper | Alvin | 2023-03-28 | Defect | Septian |  |  |  |  | Root Cause: di Codingan nya action button delete ada manggil action add logic validasi button add ada kesalahan harusnya < , utk skrg kalau 1 keatas throw error
121 | goAML - Data - Account - view - Detail | Ketika melihat detail dari account Entity grouping UInya tidak sesuai dengan saat di menu edit. dan Membuat User bingung membaca Data | Chrome | Quality | Interface | Closed | 3-Minor | Alvin | 2023-05-04 | Defect | Ripan | Ripan |  | 2023-05-04 | 2023-05-04 | Root Cause: Grouping yang tidak sesuai
122 | goAML - Data - Account/Customer - View - Edit | Anomali Pada Data "Rahman" yang berasal dari Modul Customer ketika sedang menambahkan Person Signatory pada Menu Edit. Ketika Rahman Dipilih Akan memuncul Kan "Type Cast Error". error muncul pada Customer di bagian Detail/Edit data Rahman | Chrome | Quality | Data | Retest | 2-Major | Alvin | 2023-05-04 | Defect |  |  |  | 2023-05-05 |  | Root Cause: Nullable Relation Date yang seharusnya sudah di hide belum di handle Raised pertama ke Mas Ripan Karena menemukannya di account. ternyata dampak error dari Customer. Per 5-May-23 error pada Account sudah di handle. Di Customer Berubah errornya. "Conversion from type 'DBNull' to Type 'String' is not Valid" Note : Error 4-may-23 tidak ada documentasi karena tidak sengaja tercut di word saya - Alvin
123 | goAML - Data - Customer - View - Add/Edit/Detail | Field Form Pada Relation Related Person, masih menggunakan skema yang belum di update, Refer Table skema 4.42 T.Type Person, tampilan pada Grid columnya dibuat menjadi menampilkan 3 column penting. Contoh Nama, SSN , dan Nationality | Chrome | Definition | Requirement Error | Closed | 2-Major | Alvin | 2023-05-05 | Defect
124 | goAML - Data - Customer - View - Add/Edit/Detail | Form pada Customer baik individu maupun entity, belum mempunyai field comment. sedangkan pada skema harusnya memiliki field Comment. Refer Table Skema 4.41 T. Type Person_my_client dan 4.21 T. Type entity_My_client | Chrome | Definition | Requirement Error | Closed | 2-Major | Alvin | 2023-05-05 | Defect
125 | goAML - Data - Customer - View - Add/Edit | Ketika Form Memiliki 2 data kosong, Contoh di urutan field 1 dan di urutan field 5 validasi yang ter trigger terlebih dahulu merupakan validasi yang di urutan field ke 5. Selainnya validasi tersebut berfungsi dengan normal. Lebih Baik Validasi Tersebut diurutkan dari yang paling atas | Chrome | Quality | Interface | Closed | 4-Saran | Alvin | 2023-05-05 | Defect
126 | goAML - Data Customer - View - Edit | Beberapa Grid mempunyai text yang masih berbahasa Indonesia pada menu Edit. Form Individu Data Individu Informasi telepon Informasi Address Informasi Telepon Kerja informasi Address kerja Form Corporate Data korporasi Informasi Address Informasi telepon | Chrome | Quality | Interface | Closed | 3-Minor | Alvin | 2023-05-05 | Defect
127 | goAML - Data - Customer - Approval - Detail | Di Approval muncul grid yang tidak sesuai dengan tipe data form, Contoh muncul grid related person pada data form entity, dan muncul grid related entity dan director pada form individu | Chrome | Quality | Requirement Error | Open | 2-Major | Alvin | 2023-05-05 | Defect | [5 empty] | Root Cause: modul masih belum selesai di kerjakan
128 | goAMl - Data - Customer - View - Detail | Pada Form individu, Urutan Action Button tidak sesuai dengan form yang lainnya. Action Button pada menu detail pada beberapa menu berada pada pokok Kanan atau urutan terakhir, bukan pojok kiri atau urutan pertama. yang kemungkinan akan membuat bingung user table yang terdampak: email Person PEP Related Person Sanction | Chrome | Quality | Interface | Closed | 3-Minor | Alvin | 2023-05-05 | Defect
129 | goAMl - Data - Customer - View - Add | Pada Grid penambahan Director pada Form corporate. ketika manambahkan data baru yang kosong pada Director. tidak mempunyai validasi dan akan tertambahkan pada table | Chrome | Quality | Program | Closed | 2-Major | Alvin | 2023-05-05 | Defect
130 | goAML - Data - Customer - View - Add | Pada Grid Penambahan email pada form individu. Ketika menambahkan data baru kosong pada field email. Validasi akan ter trigger namun terdapat kesalahan Info Error Validasinya "CIF is Required " | Chrome | Quality | Interface | Closed | 3-Minor | Alvin | 2023-05-05 | Defect
131 | goAML - Data - Account - Approval - Detail | Pada Detail Approval bagian grid Signatory/ Account Related Person. ketika button detail di tekan dan memunculkan detail data signatory. Button back dapat ditekan namun tidak menutup detail dari Signatory. Detail Signatory masih dapat dapat ditutup dengan button Close window sehingga tidak menggangu flow user | Chrome | Quality | Program | Closed | 3-Minor | Alvin | 2023-05-08 | Defect | Ripan |  |  | 2023-05-09
132 | goAML - Data - Account - View - Edit | Pada Menu Edit pada field Status Code, ketika memasukan data kosong lalu clock submit. Error Message mempunyai kesalahan info error validasi yang tidak sesuai dengan nama field error yang miuncul adalah "Status rekening is Required" | Chrome | Quality | Interface | Closed | 3-Minor | Alvin | 2023-05-08 | Defect | Ripan |  |  | 2023-05-09
133 | goAML - Report - Upload Report STR - View - Detail | Pada Menu Detail ketika menekan detail pada Panel Biparty / Multiparty akan muncul error "Nullable Object Must Have Value" | Chrome | Quality | Program | Closed | 2-Major | Alvin | 2023-05-16 | Defect Upload STR | Ripan |  |  | 2023-05-16 |  | Parsing Data dari table upload ke original belum di apply
134 | goAML - Report - Upload Report STR - View - Add | Ketika user menambahkan data activities baru dengan upload File Excel. meskipun file dan data yang ingin di upload sudah sesuai standard. Muncul error "Column name or Number of supplied values does not match table definition" ketika menekan tombol import | Chrome | Quality | Program | Closed | 1-Showstopper | Alvin | 2023-05-17 | Defect Upload STR | Dev Lama |  |  |  | 2023-05-17 | root cause: Terdapat kekurangan pada column didalam template excelnya. sehingga menyebabkan kesalahan pada query Insert
135 | goAML - Report - Upload Report STR - View - Detail | Panel Data Activities yang telah diupload oleh user tidak muncul pada record ketika menekan tombol detail. Data tidak masuk kedalam database setelah di approve oleh checker user | Chrome | Quality | Data | Closed | 2-Major | Alvin | 2023-05-22 | Defect Upload STR | Dev lama |  |  |  | 2023-05-22 | Root Cause: masih terdapat bug pada source code existing . approvalnya itu jalan. cuman dibagian akhir ada truncate table, klo table lain itu truncate table uploadnya. si activity yg di truncate table utamanya. makanya kosong table acivity
136 | goAML - Report - Upload Report STR - View - Add | Ketika user Menambahkan data activities baru dengan jenis laporan yang tidak valid (LTKM atau jenis laporan untuk transaksi) pada Row 1(row atas). Data Valid Activities pada row 2 (row bawah) akan terkena validasi error bahwa jenis Laporan LTKM hanya untuk transaksi meskipun sudah menggunakan jenis Laporan LAM | Chrome | Quality | Program | Closed | 1-Showstopper | Alvin | 2023-05-23 | Defect Upload STR | Dev Lama |  |  |  | 2023-05-23 | Root Cause : bug existing, issuenya di validasi data pas import. ada salah naro validasi.
137 | Proses Daily CTR | Error saat proses daily CTR: Task Detail is canceled: Invalid column name 'trn_addr_country_code'. Invalid column name 'trn_addr_country_code'. Invalid object name 'goAML_Report_Email'. Invalid object name 'goAML_Report_Email'. Invalid object name 'goAML_Report_Email'. Invalid object name 'goAML_Report_Email'. | Mozilla | Quality | Program | Closed | 1-Showstopper | Cici | 2023-05-02 | Sheet19 ¦ Proses Daily! |  |  |  | 2023-05-02 | 2023-05-02 | Root Cause: Ada perubahan nama field Country_Code -> trn_addr_country_code, tapi di beta belum di rename
138 | Proses Daily CTR | Case: Di CTR ada report sisi to dan from, disini kondisi nya global param pk 14 = 1, yg diambil yg sisi rekening. Ketika proses ulang yg kebentuk di related person itu 2 id report (123048 dan 123049) tapi pas cek di table report yang 123049 gak ada. harusnya report 123049 pindah ke Table Not Reported | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2023-05-02 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-02 | 2023-05-02
139 |  | PEP Country Related Person tidak keinsert | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2023-05-03 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-02 | 2023-05-02
140 | Proses Daily IFTI | Error Saat Proses Daily IFTI: Task Detail is canceled: The select list for the INSERT statement contains more items than the insert list. The number of SELECT values must match the number of INSERT columns. | Mozilla | Quality | Program | Closed | 1-Showstopper | Cici | 2023-05-19 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-19 | 2023-05-19 | Root Cause: Field di table existing belum naik semua ke beta
141 |  | Format Entity Reference IFTI SWIFT dan Non SWIFT berbeda | Mozilla | Quality | Program | Closed | 3-Minor | Cici | 2023-05-19 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-19 | 2023-05-19
142 | Generate SAR STR | Export Search Transaksi: Hasil Excel nya berbeda dengan Data yang di grid Search Transaksi. Hasil Excel nya export semua data di ODM | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2023-05-23 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-23 | 2023-05-23
143 |  | Is Suspected From, Is Suspected To dan Is Suspected Conductor, di ceklis saat generate str, tapi datanya gak kesimpan di table | Mozilla | Quality | Program | Closed | 2-Major | Cici | 2023-05-23 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-23 | 2023-05-23
144 |  | Error saat Approve dan Reject Generate STR | Mozilla | Quality | Program | Closed | 1-Showstopper | Cici | 2023-05-23 | Sheet19 ¦ Proses Daily! | Felix |  |  | 2023-05-23 | 2023-05-24 | Root Cause: ada update bll di account, customer dan wic, update nya berupa struktur table di define di bll. masalah nya di goaml str sar masih pake dal, dan dia detect nya ada 2 versi dal dan bll jadi ambigious. Fix: saat insert ke table pake query sql helper
145 | goAML - Data - Customer - View - Detail/Edit | Data Customer non Entity yang mempunyai isi data pada Related Person akan mengalami error "Specified Cast no Valid" ketika memasuki menekan tombol Detail/Add | Chrome | Quality | Program | Retest | 1-Showstopper | Alvin | 6-Juni-23 | Sheete 20 - Customer
146 | goAML - Data - Customer - Approval - Detail | Typo Pada New Value di menu Approval Detail. "Has Passed Awat" dimana harusnya "Has Passed Away" | Chrome | Quality | Interface | Raised | 3-Minor | Alvin | 6-Juni-23 | Sheete 20 - Customer | Ripan
147 | goAML - Data - Customer - View - Detail/Edit | Data yang berisi Customer Entity Muncul beberapa Field dan Panel pada Detail , padahal sudah di Hide pada Menu Add dan edit - Field Entity Status - Field Entity Status Date - Grid Related Person Relate ke Defect ID 127 | Chrome | Definition | Requirement Error | Raised | 2-Major | Alvin | 6-Juni-23 | Sheete 20 - Customer | Ripan
148 | goAML - Data - Customer - View - Add | Data Customer Entity Mempunyai Required Field yang tidak sesuai dengan Dokumen definisi, Refer Pada Dok Translasi Skema tabel 4.33 dan 4.44 - Pada Identity Entity - Pada Relatef Entity | Chrome | Definition | Requirement Error | Raised | 2-Major | Alvin | 6-Juni-23 | Sheete 20 - Customer | Ripan
149 | goAML - Data Customer - View/Approval - Add/Detail | Pada Data customer Entity. Ketika Menambahkan Data Related Entity dengan menggunakan Add dan lanjut ke approval dan approve. Data dari related entity akan ter insert 2x pada database menyebabkan data duplicate | Chrome | Quality | Data | Raised | 2-Major | Alvin | 6-Juni-23 | Sheete 20 - Customer
150 | goAML - Data - Customer - View - Add | Pada Form Add data customer Non Entity, terdapat field yang required. Validasi required berjalan namun tidak mempunyain tanda bahwa Field tersebut required. Field yang terdampak gender birthdate birthplace nation1 domisili / residence occupation source of wealth | Chrome | Quality | Interface | Open | 3-Minor | Alvin | 7-Juni-23 | Sheete 20 - Customer
151 | goAML - Data - Customer - Approval - Detail | Pada Detail From Approval, Click Button Detail Pada Grid memiliki berbagai error button yang terdampak : -Pada Old Value dan New Value Phone dan Address, Ketika di click menampilkan error "Object reference not set to an Instance of an Object" -Pada Old Value dan New Value Work Phone ketika di click menampilkan error "Index Was out of Range" -Pada New Value work Addres ketika di click tidak memunculkan detail dari data tersebut - Pada new value Identification ketika di click tidak memunculkan detail dari data tersebut | Chrome | Quality | Program | Open | 2-Major | Alvin | 7-Juni-23 | Sheete 20 - Customer
152 | goAML - Data - Customer - Approval - Detail | Pada Detail Form Approval. Pada grid Person PEP. Data Country didalam grid tersebut tidak muncul pada kolom preview Person PEP. namun data tersebut masuk dan dapat dilihat dengan menggunakan tombol Detail Person PEP | Chrome | Quality | Data | Open | 3-Minor | Alvin | 7-Juni-23 | Sheete 20 - Customer
153 | goAML - Data - Customer - View - Add | Pada Form Add data customer Entity, Ketika submit data tanpa memasukan data Director. Director tervalidasi Required. sedangkan Pada Skema tidak required Refer Table 4.21 Jenis t_entity_my_client bagian director ID | Chrome | Definition | Requirement Error | Open | 2-Major | Alvin | 7-Juni-23 | Sheete 20 - Customer
154 | goAML - Data - Customer - View - Add | Pada Form Add Data Customer Entity, ketika click button detail disaat data director sudah di tambahkan muncul error "Object Reference not set to an instance of an object" | Chrome | Quality | Program | Open | 2-Major | Alvin | 7-Juni-23 | Sheete 20 - Customer
155 | goAML - Data - Customer - View - Add | Pada form Add data Customer Entity, ketika menambahkan data Director, beberapa field memiliki validasi requirement yang berjalan. namun tidak memiliki tanda bahwa field tersebut required Field yang terdampak Gender Date of Birth Place of Birth Nationality 1 | Chrome | Quality | Interface | Open | 3-Minor | Alvin | 7-Juni-23 | Sheete 20 - Customer
156 | goAML - Data - Customer - Approval - Detail | Ketika melihat detail data yang baru saja di Add, data yang baru saja di add tidak dapat dilihat dalam kolom pada panel new Value. namun ketika sudah di approve data tersebut terinsert kedalam database | Chrome | Quality | Interface | Open | 3-Minor | Alvin |  | Sheete 20 - Customer
157 | goAML - Data - Customer - View - Edit | Di bagian Grid Director, Semua tombol Action mempunyai Error yang berbeda - Ketika menekan tombol Detail akan memunculkan error : "Value Cannot be Null, Parameter Name 'Source'" -Ketika Menekan tombol Edit akan memunculkan error "Object Reference not set to an Instance of an object" - Ketika menekan tombol delete akan berhasil menghapus data director dari Kolom Grid Director, lalu ketika submit data akan lolos validasi required. Pada menu approval data dari Director tersebut akan kembali lagi kedalam old value dan new value. -Add new data setelah data director telah dihapus dari Kolom akan memunculkan error "Object Reference not set to an Instance of an Object" setelah submit semua data valid dan sesuai requirement | Chrome | Quality | Program | Open | 1-Showstopper | Alvin | 7-Juni-23 | Sheete 20 - Customer
158
Note on H124: Adi Darmawan: Sebelumnya Minor. Delivery yang tidak sesuai requirement itu Major.
Note on H125: Adi Darmawan: Sebelumnya Minor.
Note on H126: Adi Darmawan: Sebelumnya Minor.

## Sheet20 - Customer
145
146
147
148
149
150
151
152
153
154
155
156
157
detail | edit | add

## Sheet19 ¦ Proses Daily
137
138
139
140
141
142
143

## Sheet17 ¦ Account
101
102
103
104
105
106

## Sheet16
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
s
17

## Sheet15
68
69
70
71
72

## Sheet13
57

## Sheet11
Error Message proses Validate Schema
Field email pada account signatory (From)
Field email pada account signatory (To)
Field email pada Conductor

## Sheet10
Defect NO
48

## Sheet9
Defect No
45

## Sheet8
Defect No
42
43
44

## Sheet7
Defect Log
21

## Sheet6
Defect Log
19
20 | Reject

## Sheet5
Defect No
18

## Sheet4
Defect No
15
16 | btw perubaha submission emng ada impact ke button view trx ya isi from account cuma isi coorporate name (gak isi director) |  |  | isi from account cuma isi coorporate name (gak isi director)
>>>>
>>>
From Not My Client keisi data director padahal sblmnya gak diisi
17

## Sheet3
Defect No
11 | Update 13/12/21
12
13

## Sheet2
Defect No
7
|  |  | --> | -->
>
setelah di cek di wic ada datanya
8
9
Cek di Account
10

## Sheet1
Tanggal Test: 071221
Defect No
1
2 | Update 081221
3
4
5
6

## Sheet17
112
113
114 dan 115
116
117 dan 118
119
120
121
Menu Detail
Menu Edit
131
132

## Sheet18
122
123
124
125
126
127
128
129
130

## Upload STR
133
134
135
136